## 90 Day Sprint
Week | Focus Area | Action | Deliverable | Status | Priority
1 | Positioning | Finalize positioning and target market | Updated website messaging |  | High
2 | Website | Update website around Digital Solutions for Engineering & Manufacturing SMEs | Website updated |  | High
3 | Research | Build target company list | 150 companies in CRM |  | High
4 | CRM | Create lead generation pipeline | Working CRM pipeline |  | High
5 | Discovery | Interview first 5 prospects | Interview notes |  | High
6 | Discovery | Interview next 5 prospects | 10 interviews completed |  | High
7 | Analysis | Document top customer pain points | Customer Pain Report |  | High
8 | Development | Improve CRM based on feedback | CRM V1 |  | High
9 | Marketing | Create CRM case study | Case Study PDF |  | Medium
10 | IoT | Build Raspberry Pi monitoring demo | IoT Demonstrator |  | Medium
11 | Roadmap | Create product architecture roadmap | Roadmap graphic |  | Medium
12 | Pilots | Launch pilot programme | First pilot customer |  | High
13 | LinkedIn | Publish industry content | 15 LinkedIn posts |  | Medium

## Sheet1
Company | Sector
Actemium UK | Automation
Boulting Group | Automation
Keyte Smith | Rail & Automation
ADI Group | Industrial Automation
Applied Integration | System Integration
Tecosim UK | Engineering
ECS Solutions | Controls
TCS Control Systems | Automation
Iconsys | System Integration
NeoDyne UK | Automation
Automation Experts | Automation
Sabeti Wain Aerospace | Aerospace Automation
Festo UK | Automation
SMC UK | Automation
Bosch Rexroth UK | Automation
Mitsubishi Electric UK | Automation
Omron Electronics UK | Automation
Rockwell Automation UK | Automation
Siemens Digital Industries UK | Automation
Schneider Electric UK | Automation
RSE | Systems Integration
M Group Water | Industrial Controls
A&E Engineering | Machine Building
Morrison Energy Services | Industrial Automation
BGEN | Controls & Automation
WSP UK | Engineering
Mott MacDonald | Engineering
AtkinsRéalis | Engineering
Apex Automation | Machine Automation
Graham Hart Process Technology | Process Automation
Industrial Automation & Control Ltd | Controls
SSE Enterprise Controls | Controls
Blackrow Group | Industrial Engineering
AstraZeneca Engineering | Manufacturing
JBT Marel UK | Machine Building
SP Technology | Automation
MSE Hiller | Machine Building
Cully Automation | Automation
Servelec Controls | Controls
Aimtec | Automation
Briggs Automation | Automation
DSEAR Solutions | Industrial Engineering
Phoenix Control Systems | Controls
Automated Control Solutions | Controls
MPE Limited | Machine Building
Autech Control Group | Controls
Integrated Control Solutions | Systems Integration
Cranston Engineering | Industrial Engineering
Saftronics | Automation
LCA Group | Automation